Operational Tooling Project – Discovery Phase Execution Plan

Focus: TIBCO Exit Program – Claims & Remit Migration, Dark-Launch Services, Comparator & Parser Strategy

Summary Table – Workstreams & Key Information

| Workstream | Primary Deliverable(s) | Suggested Owner(s) | Estimated Discovery Effort |
| --- | --- | --- | --- |
| 1 – Claims & Remit File Type Analysis | • File-type mapping matrix (current ↔ target) • Gap-analysis report • UI screen-format specifications (wire-frame level) | Lead Business Analyst, Integration Architect, UI/UX Designer | 2 weeks (Week 1-2) |
| 2 – Dark-Launch Services Technical Architecture | • Dark-Launch architecture blueprint (component diagram, data-flow) • Infrastructure & integration dependency map • Observability & alerting design | Platform Lead, Solution Architect, DevOps Engineer | 1.5 weeks (Week 2-3) |
| 3 – File-Type Comparator & Parser Understanding | • Comparator capability matrix • Parser library catalogue • Gap & build-recommendation list (new parsers/comparators) | Lead Developer, QA Lead, Architecture Analyst | 1.5 weeks (Week 3-4) |
| Cross-Cutting | • Decision Log & Open-Questions Register • Acceptance Criteria & Exit Criteria for Discovery | Delivery Manager (overall) | Continuous (throughout) |

Target Discovery Duration: 4 weeks (5 working-day sprints).
Sprint Breakdown: Week 1 – Workstream 1 kick-off & file-type inventory; Week 2 – File-type mapping & start of Dark-Launch architecture; Week 3 – Complete Dark-Launch blueprint & start comparator/parsers; Week 4 – Finalise comparator matrix, consolidate deliverables, review acceptance criteria.

1. Discovery Phase Overview

| Aspect | Details |
| --- | --- |
| Scope | Analyse all claims and remit file types produced by existing TIBCO BW orchestrations, define the dark-launch service architecture to shadow live traffic, and catalogue comparator/parsers needed for end-to-end validation. |
| Timeline | 4 weeks (20 working days). See Sprint Timeline below. |
| Team Roles | • Delivery Manager (DM) – overall coordination, risk & issue log. • Solution Architect (SA) – technical design, architecture decisions. • Integration Lead (IL) – TIBCO BW deep-dive, mapping. • Business Analyst (BA) – requirements capture, UI specs. • UI/UX Designer (UX) – screen wireframes. • DevOps Engineer (DE) – infrastructure & observability. • Lead Developer (LD) – comparator/parsers assessment. • QA Lead (QL) – validation approach. • SME – TIBCO Ops – legacy knowledge. |
| Sprint Timeline | Week 1 – Kick-off, environment onboarding, file-type inventory (WS-1). Week 2 – Mapping & gap analysis (WS-1), start dark-launch high-level design (WS-2). Week 3 – Complete dark-launch architecture, begin comparator/parsers deep-dive (WS-3). Week 4 – Finalise comparator matrix, consolidate all deliverables, stakeholder review & sign-off. |
| Reporting Cadence | Daily stand-ups (15 min), mid-sprint review (end of Week 2), sprint demo & retrospective (end of Week 4). |
| Key Success Metrics | • 100 % of in-scope file types identified and documented. • Architecture diagram approved by Platform & Security teams. • Comparator/parsers gaps captured with priority ranking. • All deliverables signed off against acceptance criteria. |

2. Environment Access & Onboarding Plan

| Step | Action | Owner | Expected Completion |
| --- | --- | --- | --- |
| 1 | Request VPN / network access to TIBCO BW-5.x and BW-6.x environments (dev, test, prod). | DM (coordination) & DE (network) | Day 2 |
| 2 | Provision read-only credentials for Enterprise Service Bus (ESB), ActiveMatrix BusinessWorks repositories, and deployment scripts. | DE | Day 3 |
| 3 | Obtain Current Deployment Architecture Documentation (C4 diagrams, infra topology). | IL | Day 4 |
| 4 | Clone Comparator Codebase (Git repo) and Parser Library Inventory (artifact repository). | LD | Day 5 |
| 5 | Set up local dev sandbox with TIBCO runtime, enable debug logging for orchestration steps. | DE & IL | Day 6 |
| 6 | Conduct Onboarding Workshop (2 h) with TIBCO SME to walk through orchestration flows, naming conventions, and any known quirks. | SME + BA | Day 7 |
| 7 | Validate access by executing a sample claim orchestration and confirming output files are generated. | IL | Day 8 |

Critical Assumption: All access requests cleared within 48 h; otherwise discovery timeline will shift by the delay amount.

3. Decision Log & Open Questions Register (Template)

| ID | Decision / Question | Owner | Date Raised | Resolution / Status | Comments |
| --- | --- | --- | --- | --- | --- |
| D-001 | Choose traffic-shadowing proxy (Envoy vs NGINX) | SA | 2026-04-14 | Pending – to be decided in WS-2 | Dependent on platform-team support for side-car injection |
| Q-001 | Are there any proprietary claim formats not yet captured in the current integration catalogue? | BA | 2026-04-14 | Open | Will be answered during file-type inventory (WS-1) |
| … | … | … | … | … | … |

The register will be maintained in a shared Confluence page and referenced in all sprint reviews.

4. Workstream 1 – Claims & Remit File Type Analysis

- Identify every claim and remit file type generated by the existing TIBCO BW orchestrations.

- Map each current file type to the target format that will be produced by the new technology stack (e.g., micro-services, Cloud-native APIs).

- Produce a gap analysis highlighting mismatches, missing fields, or format discrepancies.

- Define UI screen formats required for operational tooling (e.g., diff view, status badge, error highlights) for each distinct file type.

| # | Activity | Owner(s) | Effort (person-days) |
| --- | --- | --- | --- |
| 1 | Inventory all claim/remit file types from BW processes (review .proc files, XSDs, EDI schemas). | IL, BA | 3 |
| 2 | Extract sample payloads for each type (both successful and error cases). | IL | 2 |
| 3 | Conduct workshops with Business SMEs to confirm business meaning & required fields. | BA, SME | 2 |
| 4 | Draft Current → Target mapping matrix (format, encoding, field naming). | SA, BA | 2 |
| 5 | Identify transformation gaps (missing fields, structural changes). | SA | 1 |
| 6 | Prioritise gaps based on impact (High/Med/Low). | DM, BA | 0.5 |
| 7 | Define UI screen requirements per file type (field list, diff view, alerts). | UX, BA | 2 |
| 8 | Produce wire-frame prototypes for each screen type (e.g., Claim-Detail, Remit-Summary). | UX | 2 |
| 9 | Review matrix & UI specs with stakeholders; capture sign-off. | DM, BA, UX | 1 |
| Total |  |  | 15.5 PD |

Note: Activities 1-5 constitute the analysis; 6-9 transition to design of UI support.

- TIBCO BW project source (proc files, BPMN diagrams).

- Current deployment architecture docs (service endpoints, file routing).

- Sample claim/remit files (both success & error).

- Business rule documents (validation rules, field-level mandatory requirements).

- Target technology specifications (e.g., JSON schema, FHIR profiles, XML XSDs).

- SME availability (claims processing, remit reconciliation).

- Static Artefact Review – Parse BW process definitions to list all FileWrite/FileRead activities, capture file naming conventions, and locate associated schema references.

- Dynamic Sample Capture – Execute a set of representative claim/remit transactions in a sandbox to collect real output files; validate against identified schemas.

- Schema Comparison – Use a diff tool (e.g., XMLSpy, jsondiff) to compare current XSD/EDI definitions with target schemas, documenting field-level differences.

- Business Impact Scoring – For each identified gap, assess: (a) regulatory impact, (b) downstream system dependency, (c) effort to remediate (simple mapping vs new field generation).

- UI Requirement Derivation – Translate gap severity into UI needs: high-severity gaps ⇒ diff view with inline error highlighting; low-severity gaps ⇒ simple status badge.

The analysis will stop before any decision on transformation implementation; it will only output the evidence-based gap matrix and UI spec outline.

| Deliverable | Description |  |
| --- | --- | --- |
| File-Type Mapping Matrix | Table listing each claim/remit type, current BW output format, target format, transformation required, gap description, UI screen flag. |  |
| Gap-Analysis Report | Narrative with impact scoring, risk assessment, and recommendation of remediation approaches (to be taken forward in build phase). |  |
| UI Screen Specification Document | For each distinct file type: wire-frame diagram, field-level diff logic, status indicators, error-highlight rules. |  |
| Stakeholder Sign-off Sheet | Recorded approvals from Business, Architecture, and Operations leads. |  |
| Risk / Dependency | Impact | Mitigation |
| Access delay to BW environments | Timeline slip (≥ 2 days) | DM to raise early IT request; have fallback of archived process artefacts. |
| Incomplete legacy schema documentation | May miss obscure file variants | Conduct SME interviews; use production logs to surface hidden variants. |
| Business rule ambiguities (e.g., optional fields) | Mis-ranked gaps | Capture decisions in Decision Log; raise clarifying tickets immediately. |
| Licensing constraints on target parser libraries | Potential redesign of target format | Identify licensing status during Activity 4; involve Legal early. |

- AC-1: All claim and remit file types produced by the current TIBCO BW landscape are listed (≥ 95 % coverage verified by sample extraction).

- AC-2: Mapping matrix contains Current Format, Target Format, Transformation Needed, and Gap Flag for each entry.

- AC-3: UI screen specifications are produced for every file type that will be surfaced in the operational tooling, with reviewed wire-frames.

- AC-4: Gap-analysis report and UI spec are approved by Business Owner, Solution Architect, and Delivery Manager (sign-off captured).

Done when all four criteria are satisfied and documentation stored in the project Confluence space.

5. Workstream 2 – Dark-Launch Services Technical Architecture

- Design a complete technical architecture that enables shadow (dark) launch of the new claim/remit services alongside existing TIBCO BW processes.

- Define routing & traffic-shadowing mechanisms, comparison trigger points, alerting, and observability.

- Identify infrastructure dependencies (e.g., service mesh, message brokers) and any required integration touch-points with downstream systems.

| # | Activity | Owner(s) | Effort (PD) |
| --- | --- | --- | --- |
| 1 | Review existing production traffic flow (API gateway, MQ, file drop) | SA, DE | 1 |
| 2 | Evaluate candidate shadow-traffic technologies (Envoy mirror, NGINX mirroring, Istio traffic split) | SA, DE | 1 |
| 3 | Draft component diagram (Ingress → Shadow Proxy → New Service → Comparator → Store) | SA | 0.5 |
| 4 | Define comparison trigger (synchronous diff vs async batch) and data store (e.g., DynamoDB, PostgreSQL) | SA, LD | 0.5 |
| 5 | Design alerting thresholds (error rate, latency delta) and select observability stack (Prometheus-Grafana, Splunk, Datadog) | DE, QL | 1 |
| 6 | Identify infrastructure dependencies (certificate management, service mesh, side-car injector) | DE | 0.5 |
| 7 | Produce security & compliance checklist (data masking, PII handling in shadow traffic). | SA, Security SME | 0.5 |
| 8 | Conduct architecture review workshop with Platform, Security, and Ops leads; capture decisions. | DM, SA | 0.5 |
| Total |  |  | 5.5 PD |

- Current API gateway and MQ topology diagrams.

- Live traffic statistics (TPS, peak windows).

- Access to sandbox environment where a traffic-mirroring proxy can be installed.

- Target service contract (OpenAPI spec, gRPC proto).

- Observability tooling licences/inventory (Grafana, Splunk, etc.).

- Security policies (encryption, audit logging).

- Traffic Flow Mapping – Create a C4 Container diagram of existing ingress points (REST, SOAP, MQ) and downstream TIBCO BW services.

- Shadow-Traffic Feasibility Study – For each ingress point, evaluate if packet-level mirroring or logical request duplication is possible without impacting latency. Compare Envoy (mirroring filter) vs NGINX (mirror module) vs Istio (traffic split).

- Comparison Model Decision – Determine whether to compare synchronously (inline diff before response) or asynchronously (store both responses, run background diff). Use latency impact analysis (benchmark with 5 % traffic sample).

- Observability Gap Analysis – Map required metrics (request count, diff error rate, latency delta) to existing tooling capabilities; note any missing collectors.

- Dependency Matrix – List each architectural component and its required infra (e.g., Kubernetes cluster version, side-car injection support).

The analysis culminates in options with pros/cons; a final selected architecture will be recorded in the Decision Log (not a recommendation yet, just a documented choice made with stakeholder sign-off).

| Deliverable |  | Description |
| --- | --- | --- |
| Dark-Launch Architecture Blueprint (C4 diagram + component list). |  |  |
| Traffic-Shadowing Technology Evaluation Matrix (Envoy, NGINX, Istio, custom proxy). |  |  |
| Comparison Engine Design (sync vs async flow, data store schema). |  |  |
| Observability & Alerting Design Document (metrics, dashboards, alert thresholds). |  |  |
| Infrastructure Dependency Register (hardware, cloud services, licences). |  |  |
| Security & Compliance Checklist (PII handling, encryption at rest/in-flight). |  |  |
| Architecture Review Minutes & Decision Log entries. |  |  |
| Risk | Impact | Mitigation |
| Shadow traffic may double load on downstream systems | Potential performance degradation in production | Limit shadow to ≤ 5 % of traffic initially; use load-testing to verify capacity. |
| Regulatory restriction on exposing live claim data to non-production services | Legal compliance breach | Apply data-masking at the proxy layer; involve Legal early. |
| Platform team unable to provision side-car injector | Architecture redesign required | Keep fallback to NGINX mirroring which does not need service mesh. |
| Observability tools not integrated with new proxy | Lack of visibility on shadow traffic | Build simple Prometheus exporter as part of proxy; allocate extra DE effort. |

- AC-1: Architecture diagram approved by Platform, Security, and Ops leads.

- AC-2: Traffic-shadowing solution selected and documented with justification (performance, compliance).

- AC-3: Comparison engine design (sync/async) documented, including data-store schema.

- AC-4: Observability stack list includes all required metrics; sample dashboard mock-up created.

- AC-5: All infrastructure dependencies captured in the register and confirmed as available or provisioned.

Done when the above criteria are signed off and stored in the shared architecture repository.

6. Workstream 3 – File-Type Comparator & Parser Understanding

- Obtain a complete inventory of every file type that will be compared between the legacy TIBCO BW output and the new service output.

- Document the existing comparator framework (architecture, supported file types, diff algorithms).

- Catalogue available parser libraries for each file type, evaluate their version compatibility and licensing.

- Identify gaps where new parsers or comparator extensions are required.

| # | Activity | Owner(s) | Effort (PD) |
| --- | --- | --- | --- |
| 1 | Extract list of file types from Workstream 1 mapping matrix. | LD, BA | 0.5 |
| 2 | Review comparator codebase – locate modules, adapters, and test suites. | LD | 1 |
| 3 | Produce Comparator Capability Matrix (coverage, performance notes). | LD, QL | 1 |
| 4 | Inventory existing parser libraries (e.g., StediJS, X12.NET, Jackson, custom fixed-width parsers). | LD | 0.5 |
| 5 | Evaluate each parser for: version support, license, maintenance status, and error handling. | LD, Legal SME | 1 |
| 6 | Run sample parsing for each file type (using real files from WS-1) and record success/failure. | LD | 1 |
| 7 | Identify parser gaps (missing format, unsupported version) and comparator gaps (partial diff, no field-level mapping). | LD, QL | 0.5 |
| 8 | Prioritise gaps (High/Med/Low) based on business impact and frequency. | DM, BA | 0.5 |
| 9 | Draft Gap-Resolution Recommendation (build new parser, upgrade lib, wrap existing). | LD | 0.5 |
| Total |  |  | 6.5 PD |

- File-type mapping matrix from WS-1 (delivered).

- Comparator source code repository (including CI pipelines).

- Parser library inventory (Maven/nuget/artifactory list).

- Sample files for each type (both legacy and target).

- Licensing policy for third-party libraries.

- Static Code Inspection – Scan the comparator repo for file-type handler classes, noting which file extensions/schemas they claim to support.

- Dynamic Test Harness – Build a simple harness that loads each sample file, invokes the associated parser, and records success metrics (parse time, errors).

- Coverage Mapping – Populate a matrix that cross-references File Type ↔ Comparator Coverage ↔ Parser Library ↔ Version.

- Gap Identification – Any file type where: (a) comparator reports “partial” or “none”, OR (b) parser fails on sample → flagged as Gap.

- Risk Scoring – For each gap, assign a risk score based on (i) transaction volume, (ii) regulatory importance, (iii) effort to build/upgrade.

The analysis stops at producing the Comparator & Parser Matrix and a prioritized gap list; no implementation decisions are taken yet.

| Deliverable |  | Description |
| --- | --- | --- |
| Comparator Capability Matrix (file type, coverage level, algorithm used). |  |  |
| Parser Library Catalogue (name, version, license, maintenance status, supported formats). |  |  |
| Parser & Comparator Gap List (type, missing capability, priority, suggested resolution). |  |  |
| Sample Parsing Report (pass/fail, performance metrics). |  |  |
| Decision Log entries for any library upgrades or new parser mandates. |  |  |
| Risk | Impact | Mitigation |
| Licensing incompatibility (e.g., commercial parser required) | May need to purchase licences; budget impact. | Early legal review; evaluate open-source alternatives. |
| Legacy fixed-width parsers are undocumented | Could lead to incorrect parsing rules. | Use SME walk-through of record layouts; capture field definitions in Confluence. |
| High-volume file types (e.g., 837) cause performance bottlenecks in comparator | Delays in dark-launch reporting. | Benchmark parser/comparator with realistic load; note in Gap List. |
| Parser library version conflicts (e.g., .NET vs Java) | Build-pipeline complications. | Document version matrix; decide on single language strategy in later phases. |

- AC-1: All file types from the WS-1 mapping matrix are present in the Comparator Capability Matrix.

- AC-2: For each file type, parser success/failure is recorded with at least one successful parse for the target format.

- AC-3: Gap list includes description, priority, and proposed remedy for every uncovered capability.

- AC-4: Decision Log contains entries for any required library purchases or new parser projects.

Done when the matrices, reports, and gap list are reviewed and approved by the Lead Developer, QA Lead, and Solution Architect.

7. Cross-Workstream Artefacts & Governance

7.1 Decision Log & Open Questions Register

(see Section 3 for template – maintained continuously)

7.2 Exit Criteria for Discovery Phase

| Criterion | Description |
| --- | --- |
| All Workstreams Completed | Each WS has met its Acceptance Criteria and deliverables are signed off. |
| Stakeholder Review | Consolidated discovery report presented to Business Sponsor, Architecture Board, and Platform Ops; formal sign-off recorded. |
| Risk Register Updated | All identified risks have mitigation actions or escalation paths defined. |
| Backlog Ready for Build | High-priority items (file-type transformations, dark-launch component backlog, parser/comparator development) are captured in the program backlog with clear epics and stories. |
| Knowledge Transfer | All findings documented in Confluence; walkthrough session scheduled for build-phase teams. |

**When all rows are ticked, the project transitions to the Build / Alpha phase.

8. Appendices (Collapsible for Reference)

| File Type | Current TIBCO BW Output | Target New Tech Format | Transformation Required | Gap Identified | UI Screen Required |
| --- | --- | --- | --- | --- | --- |
| Claim-837P | Fixed-width EDI 837P (v4010) | JSON (FHIR Claim R4) | Field-re-map, code set conversion, delimiter change | Missing payer-id field in source → add mapping from custom attribute | Yes – Diff view with field-level colour coding |
| Remit-835 | ANSI X12 835 (delimited) | XML (Proprietary Remit schema v2) | Structural reshape, amount rounding, date format | None (direct mapping) | Yes – Summary screen with totals & error flag |
| Claim-277 | EDI 277 (status) | JSON (status API) | Enum translation, timestamp ISO-8601 | Status codes U99 not present in target – requires extension | No – status shown on existing claim dashboard |
| Remit-CustomFF | Fixed-width proprietary | CSV (delimited) | Column re-order, padding removal | Column AdjReason missing – needs business rule addition | Yes – Validation screen with missing-column warning |
| … | … | … | … | … | … |

Key Architecture Decision: The dark-launch routing layer must be positioned upstream of the new micro-service endpoints to guarantee zero impact on the production TIBCO path. Shadow traffic is mirrored to a side-car proxy (Envoy) that forwards the request to both the legacy BW service and the new service; the comparator runs asynchronously and writes diffs to a PostgreSQL store, feeding Grafana dashboards.

| Component | Responsibility |  | Technology Candidate |  | Owner | Status (Discovery) |
| --- | --- | --- | --- | --- | --- | --- |
| Ingress Gateway | Receives external claims/remit requests (REST/MQ). |  | Kong / API-Management |  | Platform | Existing – confirmed |
| Shadow-Traffic Proxy | Mirrors live request to new service; no response impact. |  | Envoy (mirroring filter) |  | DE | Evaluated – pending security sign-off |
| Legacy Service Adapter | Calls existing TIBCO BW process (via SOAP/HTTP). |  | Custom wrapper (Java) |  | LD | Existing – documented |
| New Service Adapter | Calls new micro-service API (JSON/FHIR). |  | Spring Boot / Node.js |  | LD | To be prototyped |
| Comparator Service | Performs diff (field-level for structured data). |  | Custom comparator (Java) |  | LD | Existing – coverage analysis ongoing |
| Diff Store | Persists comparison results for reporting. |  | PostgreSQL (JSONB) |  | DE | Selected |
| Observability Layer | Metrics, logs, alerts. |  | Prometheus + Grafana; Splunk for logs |  | DE | Design drafted |
| Alerting Engine | Fires when diff error rate > 2 % or latency delta > 200 ms. |  | Alertmanager (integrated) |  | DE | Defined in design |
| File Type |  | Existing Comparator Coverage |  | Parser Library (Current) |  | Parser Version | License | Parser Gap | New Comparator Needed? | Priority |
| EDI 837P |  | Full (header, detail, trailer) |  | StediJS X12 |  | 2.4.1 | MIT | None | No | Low |
| EDI 835 |  | Partial – header only |  | X12.Net |  | 4.0.0 | Commercial | Segment-level missing | Yes (detail diff) | High |
| JSON ClaimResponse |  | Full |  | Jackson |  | 2.15 | Apache 2.0 | None | No | Low |
| XML RemitV2 |  | None (no comparator) |  | JAXB (custom) |  | 2.3 | GPL-2 | No schema validation | Yes (XML diff) | Medium |
| Fixed-Width CustomFF |  | Full (field-by-field) |  | FlatFileParser (internal) |  | 1.0 | Proprietary | Maintenance un-clear | No (if maintained) | Medium |
| … |  | … |  | … |  | … | … | … | … | … |

Prepared By

Delivery Manager – Operational Tooling Programme

Date: 2026-04-14

End of Document

Project Timeline Overview

| Week | Phase | Key Activities | Primary Owner | Deliverable |
| --- | --- | --- | --- | --- |
| 1 | Discovery – Stakeholder & Domain Analysis | Interviews, artifact collection, data-profile kickoff | Business Analyst | Interview logs & stakeholder matrix |
| 1-2 | Discovery – File-type & Current State Assessment | Catalog file formats, profile sample sets, map existing APIs | Solution Architect + BA | File-type catalogue, current-state diagram |
| 2-3 | Architecture & Design | Backend component design, React component hierarchy, dark-launch routing model | Solution Architect | Architecture Decision Document (ADD) |
| 3-4 | Backend Sprint 1 | Ingestion framework, X12 837/835 parsers, Pydantic models | Backend Devs | Ingestion service v1, unit-test suite ≥ 70 % |
| 4-5 | Frontend Sprint 1 | UI mockups, routing, API client skeleton | Frontend Devs | React prototype (file upload + diff view) |
| 5-6 | Backend Sprint 2 | Comparison engine (strategy pattern), result store, FastAPI endpoints | Backend Devs | Comparator API v1, integration tests |
| 6-7 | Frontend Sprint 2 | Tolerance UI, exception reporting, audit log viewer | Frontend Devs | Full dashboard (overview + detail) |
| 6-7 | Integration & Contract Testing | OpenAPI contract verification, mock-service validation | QA Engineer | Integrated CI pipeline, contract test report |
| 7 | Dark-Launch Preparation | Shadow-traffic routing, data-masking pipelines, monitoring config | DevOps + Solution Architect | Dark-launch playbook, Prometheus/Grafana dashboards |
| 7-8 | Dark-Launch & Hyper-Care | Enable shadow routing, run real traffic, incident response drills | Delivery Lead + DevOps | Dark-launch go-live, hyper-care run-book |
| 8 | Project Closure | UAT sign-off, final documentation hand-over, BAU transition | Delivery Lead | Acceptance sign-off, knowledge-transfer session |

Discovery Phase — Detailed Execution Plan (Weeks 1–2)

3a. Stakeholder & Domain Analysis

Reasoning – Effective comparator design hinges on understanding what business users compare (e.g., adjudication vs. payer output) and why (regulatory audit, cost variance). Clear stakeholder mapping prevents later re-work and surfaces hidden data-governance constraints.

Actions

| Action | Owner | Due |
| --- | --- | --- |
| Identify and schedule interviews with Claims Ops SME, Remit Ops SME, Compliance Lead, IT Integration Lead, Business Owner (Product) | BA | Week 1, Day 1 |
| Prepare interview guide (see questions below) and circulate 48 h prior | BA | Week 1, Day 2 |
| Conduct 30-minute stakeholder interviews (record & transcribe) | BA | Week 1, Days 3-5 |
| Consolidate stakeholder matrix (role, decision-authority, data-ownership) | BA | Week 1, Day 5 |
| Review matrix with Delivery Lead for sign-off | Delivery Lead | Week 1, Day 6 |

Key Interview Questions

- Claims: Which X12 837 variants (Professional, Institutional, Dental) are in-scope? Frequency, volume, typical file size? Any FHIR JSON/JSON-LD usage?

- Remit: Do you receive 835 ERA files, or variations (e.g., proprietary ERA)? Are electronic funds transfers (EFT) also processed?

- Other Files: What auxiliary files (eligibility, benefit enrollment) feed into the comparator?

- Business Rules: What tolerance thresholds (e.g., dollar-level variance) trigger alerts?

- Compliance: What PHI/PII fields must be masked during dark-launch? Retention periods?

- Operational: What is the expected peak load (files/hr) and SLA for comparison results?

3b. File Type & Data Structure Analysis

Reasoning – Accurate parsing requires a catalogue that records format, schema, field-level cardinalities, and known quirks (e.g., segment delimiters). Profiling informs the choice of Python libraries and helps size the comparison engine.

Actions

- Collect Sample Set – Pull ≥ 30 representative files per identified type (837 P, 837 I, 837 D, 835, FHIR, CSV).

  - Owner: BA + IT Integration Lead

  - Deadline: Week 1, Day 5

- Catalogue File Types – Create a File-Type Register (spreadsheet) with columns: File Type, Specification, Version, Typical Size, Delimiter, Key Segments/Resources, Known Anomalies.

  - Owner: Solution Architect

  - Deadline: Week 2, Day 2

- Data Profiling – Run Python scripts using pandas, fastx12, and fhir.resources to extract field statistics (null rates, distinct counts, numeric ranges).

  - Owner: Backend Dev 1 (assist)

  - Deadline: Week 2, Day 4

- Identify “Other” Files – List any files that fall outside X12/FHIR (e.g., proprietary CSV). Flag for custom parser decision later.

Recommended Tooling

- fastx12 – fast X12 segment parsing, good for 837/835.

- fhir.resources – validated FHIR model objects.

- pandas – generic CSV/TSV profiling.

- dataprof (open-source) – quick schema inference for unknown formats.

3c. Current State Architecture Assessment

Reasoning – The dark-launch will shadow existing claim/remit ingestion pipelines. Mapping those pipelines uncovers integration touchpoints, latency windows, and data-ownership boundaries that must be respected.

Actions

| Action | Owner | Due |
| --- | --- | --- |
| Produce Current-State Diagram (systems, APIs, message buses) | Solution Architect | Week 2, Day 3 |
| Document API contracts (request/response schemas, auth) of existing services used for claim/remit receipt | BA + Integration Lead | Week 2, Day 4 |
| Capture data-flow matrix (source → transform → store) for each file type | BA | Week 2, Day 5 |
| Highlight integration points where dark-launch traffic will be mirrored (e.g., Kafka topic, MQ queue) | Solution Architect | Week 2, Day 5 |
| Identify gap (missing metrics, missing audit logs) and list required enhancements | Delivery Lead | Week 2, Day 6 |

3d. Comparator Tooling Requirements Gathering

Reasoning – Translating business needs into precise functional and non-functional requirements avoids scope creep. Early definition of tolerance logic and auditability shapes the Python engine design and React UI components.

Functional Requirements (sample)

- Field-level diff – Show per-field value, status (Match/ mismatch/ missing).

- Tolerance thresholds – Configurable numeric/percentage tolerance per field (e.g., $5 amount variance).

- Exception reporting – Auto-generate CSV/JSON exception files for mismatches above tolerance.

- Batch processing – Accept multi-file upload (ZIP or streaming) and produce consolidated report.

Non-Functional Requirements

- Performance – Process 10 MB file ≤ 1 s; sustain 200 files/minute in dark-launch.

- Scalability – Horizontal scaling via Docker/K8s; stateless backend pods.

- Auditability – Immutable audit log (append-only) stored in write-once object store (e.g., S3 with Object Lock).

- Security – End-to-end TLS, OAuth 2.0 JWT for API, data-at-rest encryption (AES-256).

- Observability – Prometheus metrics (latency, error rates), Grafana dashboards, structured JSON logs.

UI/UX Requirements

- Dashboard with Upload panel, Progress bar, Result Summary (pass/fail count).

- Diff Viewer – Expandable tree view for hierarchical files (FHIR).

- Settings page – Manage tolerance config per field, user role permissions.

- Export – Download exception CSV, JSON, and PDF summary.

3e. Dark Launch Architecture Discovery

Reasoning – Dark launch imposes a shadow-traffic routing layer that must be isolated (no side-effects) yet reflect production load. Understanding existing message transport (e.g., Kafka, MQ, HTTP) determines the feasible mirroring technique.

Key Questions

- Which transport carries claim/remit files to the production comparator (file drop-zone, API, streaming)?

- Is there an existing topic we can duplicate (e.g., Kafka claims_raw) or do we need a tap at the source system?

- What masking rules are required before shadow traffic hits the new service? (e.g., replace SSN with hash).

- Who owns the routing configuration (DevOps or Integration team)?

- What failure-mode is acceptable (e.g., drop shadow traffic if latency > 2 s)?

Risk Surface

- Data leakage – Real PHI may be logged inadvertently.

- Performance impact – Mirroring could double inbound load on upstream systems.

- Version drift – If source schema changes mid-dark-launch, the comparator may crash.

3f. Discovery Deliverables Checklist

| # | Artefact | Owner | Acceptance Criteria |
| --- | --- | --- | --- |
| 1 | Stakeholder Matrix | BA | All identified roles listed; decision-authority flagged; signed off by Delivery Lead |
| 2 | Interview Summary Report | BA | Recorded transcripts, key insights extracted, distributed to team |
| 3 | File-Type Register | Solution Architect | ≥ 95 % of observed file types captured; includes delimiter, version, anomaly notes |
| 4 | Data Profiling Report | Backend Dev 1 | Sample of field statistics for each type; identifies PII fields for masking |
| 5 | Current-State Architecture Diagram | Solution Architect | Shows all systems, APIs, data flows; validated by Integration Lead |
| 6 | API Contract Inventory | BA | List of all inbound/outbound APIs with schema (OpenAPI 3.0); reviewed by Backend Devs |
| 7 | Functional & Non-Functional Requirements Document | BA + Solution Architect | All requirements from Section 3d captured; signed off by Product Owner |
| 8 | Dark-Launch Scope Definition | Solution Architect | Clear statement of shadow traffic source, routing mechanism, masking rules |
| 9 | Risk Register (initial) | Delivery Lead | ≥ 8 high-level risks identified; mitigation draft attached |
| 10 | Discovery Sign-off Pack | Delivery Lead | All above artefacts compiled, version-controlled, and stored in repo project/discovery/ |

4. Architecture & Design Phase (Weeks 2–3)

4a. Python Backend Comparator — Architecture Decisions

Reasoning – The backend must ingest heterogeneous files, parse them into canonical models, compare per configurable rules, and expose results via REST. A modular, pluggable design (Strategy pattern) enables future file-type extensions without code re-write.

Proposed Component Breakdown

| Component | Responsibility | Suggested Implementation |
| --- | --- | --- |
| Ingestion Service | Accept file streams (HTTP multipart, S3 event, Kafka consumer) and store temporarily in a processing bucket | FastAPI endpoint POST /ingest; async worker (Celery with Redis broker) |
| Parser Registry | Resolve file type → appropriate parser (strategy) | Python Strategy pattern; registry map { "837P": X12837Parser, "FHIR": FHIRParser } |
| Parser Implementations | Convert raw file → Pydantic models (validated schemas) | fastx12 for X12, fhir.resources for FHIR, custom CSV parser using pandas |
| Comparison Engine | Execute field-level diff using tolerance config; produce diff objects | deepdiff for structural diff + custom tolerance wrapper |
| Result Store | Persist diff results and audit logs (immutable) | PostgreSQL (JSONB column) for queryable diffs + S3 object lock for raw logs |
| API Layer | CRUD for diff results, tolerance config, health checks | FastAPI with OpenAPI schema, JWT auth |
| Monitoring Hook | Emit Prometheus metrics (latency, error count) | prometheus_client library |

Key Design Decisions & Rationale

- Strategy Pattern for Parsers – Allows adding new file handlers (e.g., proprietary CSV) without touching the core engine.

- Pydantic Models – Provide runtime validation and automatic OpenAPI generation, reducing boilerplate.

- DeepDiff vs Hand-rolled – deepdiff handles nested structures out-of-the box; we only need a thin tolerance layer on numeric fields.

- Celery Workers – Decouples ingestion latency from comparison; enables horizontal scaling.

Recommended Libraries

| Library | Purpose | Justification |
| --- | --- | --- |
| fastapi | API framework | High performance, async, auto-docs (OpenAPI). |
| pydantic | Data validation | Strong typing, aligns with FastAPI. |
| fastx12 | X12 parsing | Fast, handles delimiters, segment loops. |
| fhir.resources | FHIR model handling | Official FHIR STU3/R4 resources. |
| deepdiff | Structural diff | Handles nested dicts/lists, customizable. |
| celery[redis] | Async task queue | Proven, easy to containerise. |
| prometheus_client | Metrics exposure | Standard for K8s monitoring. |
| sqlalchemy + psycopg2 | DB ORM/driver | Portable, supports JSONB. |

4b. React JS Frontend — Architecture Decisions

Reasoning – The UI must be responsive, state-driven, and capable of rendering large diff trees without blocking. Leveraging React Query for data fetching and Redux Toolkit (or context) for global tolerance config ensures a predictable data flow.

Component Hierarchy (high-level)

App

├─ Header

├─ NavSidebar

├─ Dashboard

│    ├─ UploadPanel

│    ├─ JobList

│    └─ SummaryCards

├─ DiffViewer

│    ├─ TreeNode (recursive)

│    └─ FieldDetailPanel

├─ Settings

│    └─ ToleranceGrid

└─ Footer

State Management

| Concern | Technique | Reason |
| --- | --- | --- |
| Global tolerance config | Redux Toolkit slice (toleranceSlice) | Central, easy to persist to backend via async thunk |
| API data (jobs, diffs) | React Query (useQuery, useMutation) | Caching, automatic retries, background refetch |
| UI state (selected node) | Local component state (useState) | Simple, low overhead |
| Auth token | React Context (AuthProvider) | Accessible by all fetch hooks |

API Contract – Defined in OpenAPI 3.0 from backend (auto-generated). Frontend will use /jobs, /jobs/{id}/diff, /settings/tolerance. All endpoints return JSON; error payload follows Problem Details (RFC 7807).

Key UI Screens to Design

- Upload & Progress – Drag-and-drop, validation feedback, progress bar.

- Job List – Table of recent comparisons with status, runtime, pass/fail counts.

- Diff Viewer – Expandable tree; colour-code match (green), mismatch (red), tolerance-passed (amber).

- Settings – Editable grid of field-level tolerance values; versioned per client.

- Audit Log Viewer – Searchable list of job IDs with download link for raw log.

4c. Dark Launch Service Architecture

Reasoning – Dark launch must run in parallel without affecting production outputs. The simplest, low-risk approach is shadow-topic replication in the existing message broker (Kafka). If the environment uses file-drop zones, a filesystem watcher that copies incoming files to a separate “shadow” bucket works equally well.

Architecture Description (structured prose)

| Layer | Component | Responsibility | Technology |
| --- | --- | --- | --- |
| Ingress | Shadow Router | Subscribes to production topic (claims_raw) and republishes identical messages to claims_raw_shadow (Kafka) or copies files from /inbound/claims to /shadow/claims. | Kafka MirrorMaker 2 (if Kafka), fswatch + S3 copy script (if file-based) |
| Processing | Comparator Service (Blue) | Consumes from *_shadow topics / shadow bucket, runs full comparison pipeline. | Python FastAPI + Celery workers |
| Isolation Controls | Masking Service (optional) | Applies PII/PHI hashing (e.g., SHA-256) on selected fields before they reach the comparator. | Python library hashids or custom function |
| Observability | Metrics Exporter | Publishes latency, error, and mismatch counts to Prometheus. | prometheus_client |
| Data Store | Shadow Result Store | Stores diff results separately (different schema namespace) to avoid contaminating production analytics. | PostgreSQL schema shadow_ |
| Control Plane | Feature Flag Service | Enables/disables shadow consumption per environment. | LaunchDarkly (or open-source unleash) |
| Alerting | Alert Manager | Fires alerts on error spikes, high latency, or data-leak detection. | Prometheus Alertmanager + PagerDuty integration |

Traffic Routing Strategy –

- Kafka: MirrorMaker replicates all messages; the shadow consumer group (comparator-shadow) reads independently.

- File-Based: A cron/inotify daemon picks up new files, copies to shadow bucket, then triggers comparator via S3 event.

Data Isolation & Safety Controls

- Separate database schema (shadow_) ensures no cross-pollution.

- Row-level security (PostgreSQL policies) restricts who can query shadow data.

- All logs written to a dedicated S3 bucket with Object Lock for immutability.

4d. Architecture Deliverables

| Deliverable | Owner | Acceptance Criteria |
| --- | --- | --- |
| Architecture Decision Document (ADD) | Solution Architect | Includes component tables, design rationales, alternatives considered, and sign-off from Technical Lead |
| OpenAPI Spec (v1) | Backend Dev 1 | Valid YAML, passes lint (speccy), includes auth & error models |
| Component Interaction Diagram (textual description + table) | Solution Architect | Reviewed by all leads, stored in docs/architecture/ |
| Dark-Launch Playbook (routing, masking, rollback) | DevOps Engineer | Tested in staging; includes step-by-step enable/disable commands |

5. Development Plan (Weeks 3–6)

5a. Backend Development Sprints (Python)

| Sprint | Weeks | Target Features | Rationale |
| --- | --- | --- | --- |
| Sprint B1 | 3 (Mon-Fri) | • Project scaffolding (FastAPI, Dockerfile) • Ingestion endpoint (multipart upload) • Celery worker skeleton • Basic X12 837 parser (Professional) | Ingestion is the gateway; need it early to test file flow. |
| Sprint B2 | 4 (Mon-Fri) | • Complete X12 837 parsers (Institutional, Dental) • FHIR parser stub (resource to Pydantic) • Result store schema (diff JSONB + audit log) | Coverage of all claims formats before comparison logic. |
| Sprint B3 | 5 (Mon-Fri) | • Comparison Engine core (deepdiff + tolerance wrapper) • API endpoints /jobs, /jobs/{id}/diff • Unit tests ≥ 80 % for parsers & engine | Core business value – field-level diff and tolerance handling. |
| Sprint B4 | 6 (Mon-Fri) | • Remit (X12 835) parser & integration • Configurable tolerance service (CRUD) • Prometheus metrics & health checks | Adds remit coverage and operational observability before UI integration. |

Prioritisation Rationale

- Parsing precedes comparison because without reliable models diff cannot be trusted.

- Remit added after claims because claims are higher-volume and carry stricter compliance needs; this order prevents bottlenecks.

5b. Frontend Development Sprints (React JS)

| Sprint | Weeks | Target Features | Dependencies |
| --- | --- | --- | --- |
| Sprint F1 | 4 (Mon-Fri) | • Project setup (Vite, TypeScript, ESLint) • Scaffold Layout (Header, Sidebar) • UploadPanel UI (mock API) | Backend /ingest endpoint stub (returns job-id). |
| Sprint F2 | 5 (Mon-Fri) | • JobList table with pagination • DiffViewer component (tree rendering) using mock diff data • Settings page (tolerance grid) | Backend /jobs and /jobs/{id}/diff must return JSON shape (can be stubbed). |
| Sprint F3 | 6 (Mon-Fri) | • Full API integration (React Query hooks) • Real-time progress indicator (WebSocket or SSE) • Export actions (CSV/JSON) | Backend API V1 stable; Auth token flow implemented. |

Dependency Management – Frontend sprint F1 uses Mock Service Worker (MSW) to simulate API responses, enabling UI work before actual backend endpoints are live. Integration begins in Sprint F2 once the backend provides stub OpenAPI spec.

5c. Integration Milestones

| Milestone | Week | Activity | Owner |
| --- | --- | --- | --- |
| Int-1 | 5 (Wed) | Backend API contract test (OpenAPI-validator) against stubbed frontend calls | QA Engineer |
| Int-2 | 6 (Mon) | End-to-end file upload → diff result flow in staging environment | Delivery Lead |
| Int-3 | 6 (Fri) | Contract test suite passed (≥ 95 % success) for all endpoints | QA Engineer |

Contract Testing Approach – Use Pact (Python provider, JS consumer) to generate consumer contracts from frontend MSW definitions and verify provider compliance during CI.

6. Testing Strategy (Weeks 6–7)

6.1 Unit Testing (Python)

- Framework: pytest + pytest-cov.

- Coverage Goal: ≥ 85 % for parsers, ≥ 80 % for comparison engine.

- Test Cases:

  - Valid X12 837/835 with standard delimiters.

  - Edge cases (missing mandatory segments, extra optional fields).

  - Tolerance logic: numeric within/outside threshold, string case-insensitivity.

  - Masking function validation (hash output deterministic).

6.2 Integration / End-to-End Testing

| Test Type | Scope | Tools | Acceptance Criteria |
| --- | --- | --- | --- |
| API Contract Tests | FastAPI spec vs. consumer expectations | pact-provider-verifier | All contracts pass in CI |
| File-Flow Tests | Ingestion → parser → comparator → DB storage | Docker-compose test harness (Kafka mock or S3 local) | End-to-end latency ≤ 1 s for 10 MB file |
| UI-Backend Integration | React Query data fetches, diff rendering | Cypress E2E | No UI errors; diff tree matches backend payload |
| Performance Load | 200 files/min, concurrent users (3) | Locust (Python) | 95 th-percentile latency ≤ 1.5 s, error rate ≤ 1 % |

6.3 UAT Criteria

- All functional requirements from Section 3d met (field-level diff, tolerance alerts, export).

- Non-functional: Latency, scalability, audit log integrity verified.

- Compliance: No PHI logged in plain text; masking verified on 100 % of test files.

6.4 Dark-Launch Validation Testing

- Deploy comparator to shadow namespace (K8s shadow- prefix).

- Enable shadow routing for 10 % of production traffic (gradual ramp).

- Validate that shadow result set matches manual baseline for 50 sample files.

- Confirm monitoring alerts fire on any mismatch > tolerance.

6.5 Test Data Strategy

| Data Type | Source | Treatment |
| --- | --- | --- |
| Synthetic | Generated via faker & X12-template scripts | Used for unit & performance tests (no PHI). |
| Anonymised Production | Subset of live claims/remit (masked via hash on SSN, DOB) | Used for UAT & dark-launch validation. |
| Edge Cases | Manually crafted files with missing segments, malformed delimiters | Used for robustness testing. |

All test data stored in Git-LFS with read-only access; production data never checked in.

7. Dark Launch & Hyper-Care Phase (Weeks 7–8)

7.1 Dark Launch Execution Steps

| Step | Action | Owner | Timing |
| --- | --- | --- | --- |
| DL-1 | Deploy comparator service to shadow K8s namespace (shadow-comparator) | DevOps | Week 7, Day 1 |
| DL-2 | Enable shadow routing (Kafka MirrorMaker config or file copy script) for 5 % of traffic | DevOps | Week 7, Day 2 |
| DL-3 | Verify masking pipeline – spot-check 10 shadow files for hashed PII | QA Engineer | Week 7, Day 3 |
| DL-4 | Activate Prometheus alerts for error rate > 2 % or latency > 2 s | DevOps | Week 7, Day 3 |
| DL-5 | Ramp traffic to 20 %, monitor dashboards, capture diff result stats | Delivery Lead | Week 7, Day 4 |
| DL-6 | Full-scale shadow (100 %) if KPIs met; document any drift | Delivery Lead | Week 7, Day 5 |
| DL-7 | Freeze dark-launch configuration for hyper-care hand-off | DevOps | Week 8, Day 1 |

7.2 Monitoring & Alerting

- Metrics: comparator_request_duration_seconds, comparator_errors_total, shadow_mismatch_ratio.

- Dashboards: Grafana panels for latency heatmap, error spikes, PII-masking audit count.

- Alert Rules:

  - severity: critical – error rate > 5 % for > 5 min.

  - severity: warning – latency 95th percentile > 2 s.

  - severity: critical – any PHI detected in logs (regex match).

7.3 Hyper-Care SLA & Escalation

| Issue Type | SLA (post-launch) | Primary Owner | Escalation Path |
| --- | --- | --- | --- |
| Critical service outage (service down) | 30 min | DevOps Engineer | → Delivery Lead → CTO |
| Data-masking breach | 15 min | QA Engineer | → Compliance Officer → Legal |
| Performance degradation (latency > 2 s) | 1 hour | Backend Lead | → Solution Architect → VP of Engineering |
| UI rendering failure | 2 hours | Frontend Lead | → Delivery Lead → Product Owner |

7.4 Completion & BAU Transition

- Project Close-out Checklist – All artifacts signed off, runbooks stored in ops/.

- Knowledge Transfer Session – 2-hour hands-on walkthrough with BAU support team.

- Production Cut-over Decision – If dark-launch meets all KPIs for 48 h, issue “Go-Live” request.

8. Milestones Summary Table

| Milestone ID | Milestone Name | Target Week | Owner | Success Criteria | Status Tracking Method |
| --- | --- | --- | --- | --- | --- |
| M1 | Stakeholder Matrix Completed | 1 | Business Analyst | All roles captured, signed off | Confluence page |
| M2 | File-Type Register Finalised | 2 | Solution Architect | ≥ 95 % of observed formats catalogued | Git repo master |
| M3 | Architecture Decision Document (ADD) | 3 | Solution Architect | Approved by Technical Lead | PDF in docs/ |
| M4 | Backend Ingestion Service v1 Deployed | 3 | Backend Dev 1 | Unit tests ≥ 80 % + CI pass | Jenkins pipeline |
| M5 | Frontend UploadPanel Prototype | 4 | Frontend Dev 1 | UI mock passes stakeholder demo | Storybook |
| M6 | Comparison Engine v1 Ready | 5 | Backend Dev 2 | Tolerance logic matches spec for 100 test cases | Test report |
| M7 | Integrated End-to-End Flow (Staging) | 6 | Delivery Lead | Upload → diff view works without errors | Demo checklist |
| M8 | Dark Launch Shadow Traffic 100 % | 7 | DevOps Engineer | KPI: latency ≤ 1 s, error < 1 % | Grafana alerts |
| M9 | UAT Sign-off | 8 | Product Owner | All requirements met, sign-off email | JIRA ticket |
| M10 | Hyper-Care Transition Completed | 8 | Delivery Lead | Runbooks delivered, knowledge-transfer logged | Acceptance sign-off form |

9. Risks, Mitigations & Contingencies

| Risk ID | Risk Description | Likelihood | Impact | Risk Owner | Mitigation Strategy | Contingency Plan | Trigger Point |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Incomplete file-type inventory (missing rare variant) | Medium | High | Business Analyst | Early sample collection of ≥ 30 files per type; include “unknown” bucket for ad-hoc analysis | Schedule an extra 2-day deep-dive in Week 2 if > 5 % of samples unrecognised | < 5 % of sampled files classified |
| R2 | Stakeholder unavailability (SME on vacation) | Low | High | Delivery Lead | Pre-book interview windows; have backup SME (peer) | Extend discovery by 1 day, use existing documentation | No interview completed by Day 4 of Week 1 |
| R3 | Parser failure on malformed X12 | Medium | Medium | Backend Lead | Robust error handling; unit tests for malformed cases; fallback to “raw dump” mode | Switch to manual inspection for affected files; log and continue | > 2 % parsing errors in load test |
| R4 | Dark-launch traffic overload (doubling inbound load) | Low | High | DevOps Engineer | Mirror only 10 % initially; monitor upstream queue depth | Pause shadow routing, roll back MirrorMaker config | Queue depth > 150 % of baseline |
| R5 | PII leakage in logs | Low | Critical | QA Engineer | Centralised logging filter (pydantic models exclude PII); run log-scrubber CI step | Shut down logging, re-configure log level to WARN | Any log line matches PHI regex |
| R6 | Performance not meeting 1 s latency | Medium | High | Backend Lead | Profile parsers with cProfile; optional C-extension (lxml for XML) | Scale out Celery workers, add more pods | Latency > 1.2 s in staging load test |
| R7 | Tolerance configuration drift (UI updates not persisted) | Low | Medium | Frontend Lead | Use optimistic UI with ETag validation; backend versioned config | Reload config from DB on each request | UI shows stale values after edit |
| R8 | Scope creep (extra file type added) | High | Medium | Product Owner | Freeze scope in Week 2 sign-off; record change request in Change Control Board | Defer addition to Phase 2 (post-go-live) | New file-type request after Week 2 |
| R9 | API contract drift (backend changes not reflected in frontend) | Medium | High | QA Engineer | Contract testing with Pact; CI gate on both sides | Regenerate TypeScript client from OpenAPI, re-run integration tests | Pact verification fails |
| R10 | Infrastructure provisioning delay (K8s cluster not ready) | Low | High | DevOps Engineer | Reserve pre-approved sandbox cluster; use Terraform plan early | Switch to Docker-Compose local environment for development |  |